## Sheet1
| Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
FYP 1
Requirements Gathering | bar: Feb to Mar
Literature Review | bar: Mar to Apr
System Analysis | bar: Apr
System Design | bar: Apr to May
PSM I Report Writing | bar: May
PSM I Presentation | bar: Jun
FYP 2
Iteration 1: Core Modules | bar: Jul
Iteration 2: Advanced Features | bar: Aug to Sep
Iteration 3: Polish | bar: Sep
Testing | bar: Sep
Deployment | bar: Sep to Oct
PSM II Report Writing | bar: Oct
PSM II Presentation | bar: Nov